## Research Questions
Need Analysis | What are the needs of of the DIET Faculty with respect to a) Faculty Development b) Resources c) planning d)academic and e) research support
Processes | What are the process aspects that enhance / constrain engagement of stakeholders in the DRC in the following areas a) DRC Activities and functioning b) process documentation and c) resources - nature, availability d) capacity building
Impact People | To what extent and in what ways have the DRC been useful to its stakeholders a) Teacher Educators b) Student Teachers c) teachers d) BRP/CRP(?).
Impact System | To what extent and in what ways have the DRCs impacted a) DIET- School connections b) DIET and other TEIs ?

## Research Tasks
TASK | DATA REQUIRED | METHOD OF DATA COLLECTION | FREQUENCY | PERSON RESPONSIBLE
Baseline Data |  |  | One-time, beginning of project | Subject Facilitators + Field Coordinator
Faculty Profile | Education Qualifications, Experience 9school/TEI, Job profile at DIET | Surveys and Secondary Data available in the DIETs/DSERT
District Data | Blocks/Clusters/Schools/ Education Development Index | DISE Data and Survey
DIET | Infrastructure, Resources, positions filled , vacancies | Surveys and Secondary Data available in the DIETs/DSERT
DIET Programmes Data | INSET, PSTE, School Improvement, External projects | Surveys and Secondary Data available in the DIETs/DSERT
Needs Analysis
Faculty Development | Requirements and needs - capacity building, resources and expectations from system | Interview and Focus Group Discussions | One-time, beginning of project | Mythili and Bindu with TMF external assessor and DSERT representative
PSTE | Planning, Academic and Research support
INSET | Planning, Academic and Research support
School Improvement | Planning, Academic and Research support
Process Documentation
Templates for TRC setup and maintanance , running / recording and reporting
Templates for INSET preparation, running, feedback and reporting; planning, academic and research support
Templates for PSTE Planning, academic and research support
Impact
needs
content enrichment
research
mentoring
pedagogic needs
diet improvement