Meeting attendees : Mr. Manjunath , DSERT, Bindu & Sunil , TISS

Meeting Venue - DSERT

Meeting Date - 3/10/2019

Meeting Agenda: Plan for Seminar

- DRC proposal have been recommended by SPD and forwarded to principal secretary. Manjunath will email us by the end of the week , as Sec was not in station till 25th.

- SEMINAR

- DSERT will invite 5 faculty including principal from each of the 30 DIETs, total of 150 members

- 50 external participants invited from DSERT and TISS. Maximum 200 participants to be invited

- DSERT would like to invite the Education Minister Suresh Kumar  to inaugurate the function

- Tentative dates December 12th and 13th Manjunath to confirm

- Keynote speaker - familiarity with Kannada , discuss the importance of research and motivate DIET faculty

- Tentative Agenda suggested

  - Day  1

    - Morning - Inauguration

    - Afternoon - Keynote speaker

    - Panel discussion - Topic - Teacher education - 1 TISS faculty + 3 to 4 DIET faculty who have been invited to present (from previous (first)  PGCCERP batch)

  - Day 2

    - Morning - Panel discussion - Topic - Language - 1 TISS faculty + 3 to 4 DIET faculty who have completed pedagogy research of PGCCERP

    - Morning - Panel discussion - Topic - Mathematics - 1 TISS faculty + 3 to 4 DIET faculty who have completed pedagogy research of PGCCERP

    - Afternoon - Panel discussion - Topic - Science - 1 TISS faculty + 3 to 4 DIET faculty who have completed pedagogy research of PGCCERP

    - Afternoon - Closing

- Venue Shiksharaka Sadana - Manjunath will organise

- DSERT will organise a video conference to discuss with DIETs about Seminar

- Keynote speaker and panel discussion to be organised by TISS

- TISS to invite participants to write papers for seminar, to give a template and assist teachers

- A compendium to be released of all the selected research papers to be prepared

- Expenses of seminar will be borne by  DSERT including honorarium and travel for keynote speaker and panel faculty

- Open questions -

  - Will all the DIET faculty receive PGCCERP certificates during the inauguration ?

  - Suggestions on inviting the minister

- Immediate Next steps

  - Manjunath to finalise dates  and fix venue once we are all okay with it

  - TISS to send out call for papers