Meeting - Commencement of DRC programme 31/1/19

Attendees: Manjunath DSERT, Bindu TISS

Agenda :

- Release of finances - TISS expenses as suggested by Mythili

- MOU between DSERT and TISS

- Nodal DRC officers for each DIET

- DIET Proposal required from all 4 DIETs

- DSERT Librarian

- Padma GT - Studio requirement and meeting with DSERT Librarian

Letter - https://drive.google.com/open?id=1cQ-LCZ_hulH7ePO0sCJPjDC4GvU2EvcR

Meeting Notes

- Release of finances

  - Manjunath asked for clarifications of budget and a letter immediately to DSERT director asking for release of payment as TISS expenses.

  - Padma had suggested we do the first meeting in Chamrajnagar in the morning, Manjunath suggested to be included in letter

  - Manjunath to put up letter on 1/2/2019

- Manjunath & Bindu agreed that an MOU would be useful. Manjunath suggested a 3-year MOU

  - Manjunath suggested that we include request for MOU in the letter to director

  - Mythili to share sample MOU with Bindu

- Manjunath to convey that all DIETS assign a Nodal officer as DRC in charge who will participate in the programme

- Manjunath to share Bellary and Dharwad proposal and ask Mysore and Davangere DIETs to write proposal. PSTE - Bellary and Davingere as there is student strength and TPD - Mysore and Dharwad

- Manjunath suggested 12, 13 as the first workshop dates , all DRC nodal offices, Manjunath and TISS team will meet in Chamrajnagar. Manjunath to organise and convey to hosts

- DSERT librarian is not available for next few days, away on training. Bindu needs to talk to Padma GT and set up a meeting.

  - Mythili to suggest how to work with Padma GT

- Bindu to check with Padma G.T on Videos - duration , numbers and dates. Manjunath to book DSERT studio for the same

- OER workshops - we need to synergise with e-content team - Usha DSERT before planning OER workshops. Tentatively following will host OER workshops  Mysore - Maths; Davangere - Language and Social Science ; Dharwad - Science; Bellary ICT/OER. Bindu to set up meeting with Usha