## Implementation Plan GDAS
Award Number: CS/KBL/09/20/055 Project Location: Kabul Afghanistan Project Title: AQL - GDAS Competency-Based Professional Development (Training Packages) Project Start Date: April 2021 Project End Date: August 2021
Objective | Activity | Responsible | Status | Traffic Light (Red, Yellow, Green) | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3
Project Set up
Contracting completed | Complete contracting with client | SMC Leadership | Done | Done | bar: April 1
| Complete contract with Consultants | SMC Leadership | Done | Done | bar: April 2 to April 3
TWG set up | Idenify key responsibilties of TWG members and obtain agreement | Project Coordinator/ Manager & AQLC | Done | Done | bar: April 4
| Get clearance on modality | Project Coordinator/ Manager & AQLC | Done | Done | bar: April 4
| Hold official first meeting with TWG and introduce consultants | Project Development team and AQLC | in progress | in progress | bar: April 4 to May 1
Inception report development and approval | Draft inception report | SMC | Done | Done | bar: May 1
| Submit to client | SMC | Done | Done | bar: May 1
| Provide approval | AQLC | in progress | in progress | bar: May 1
Set-up Activities | Training outlines Developed | Content Development Team | Done | Done | bar: May 1
| Approval obtained from client | Project Coordinator/ Manager | in progress | in progress | bar: May 1 to May 2
| Module Framework Template Developed | Content Development Team | in progress | in progress | bar: May 1
Content Development
#REF! | Module Framework Developed | Content Development Team | in progress | in progress | bar: May 2
| Draft Development | Content Development Team | in progress | in progress | bar: May 2 to May 4
| Review and Feedback | TWG | bar: May 4 to June 1
| Adjustment | Content Development Team | bar: June 1 to June 2
| Translation | Translation Team | bar: June 2 to June 3
#REF! | Module Framework Developed | Content Development Team | bar: May 3
| Draft Development | Content Development Team | bar: May 3 to June 1
| Review and Feedback | TWG | bar: June 1 to June 2
| Adjustment | Content Development Team | bar: June 2 to June 3
| Translation | Translation Team | bar: June 3 to July 1
#REF! | Module Framework Developed | Content Development Team | bar: May 4
| Draft Development | Content Development Team | bar: May 4 to June 2
| Review and Feedback | TWG | bar: June 2 to June 3
| Adjustment | Content Development Team | bar: June 3 to June 4
| Translation | Translation Team | bar: June 4 to July 2
#REF! | Module Framework Developed | Content Development Team | bar: May 4
| Draft Development | Content Development Team | bar: May 4 to June 1
| Review and Feedback | TWG | bar: June 1 to June 2
| Adjustment | Content Development Team | bar: June 2 to June 3
| Translation | Translation Team | bar: June 3 to July 1
#REF! | Module Framework Developed | Content Development Team | bar: May 3
| Draft Development | Content Development Team | bar: May 3 to June 3
| Review and Feedback | TWG | bar: June 2 to June 4
| Adjustment | Content Development Team | bar: June 3 to June 4
| Translation | Translation Team | bar: June 4 to July 3
#REF! | Module Framework Developed | Content Development Team | bar: June 2
| Draft Development | Content Development Team | bar: June 2 to June 4
| Review and Feedback | TWG | bar: June 4 to July 1
| Adjustment | Content Development Team | bar: July 1 to July 2
| Translation | Translation Team | bar: July 2 to July 4
#REF! | Module Framework Developed | Content Development Team | bar: June 1
| Draft Development | Content Development Team | bar: June 1 to June 2
| Review and Feedback | TWG | bar: June 2 to June 3
| Adjustment | Content Development Team | bar: June 3 to June 4
| Translation | Translation Team | bar: June 4 to July 2
#REF! | Module Framework Developed | Content Development Team | bar: May 3
| Draft Development | Content Development Team | bar: May 3 to June 1
| Review and Feedback | TWG | bar: June 1 to June 2
| Adjustment | Content Development Team | bar: June 2 to June 3
| Translation | Translation Team | bar: June 3 to July 1
#REF! | Module Framework Developed | Content Development Team | bar: May 4
| Draft Development | Content Development Team | bar: May 4 to June 2
| Review and Feedback | TWG | bar: June 2 to June 3
| Adjustment | Content Development Team | bar: June 3 to June 4
| Translation | Translation Team | bar: June 3 to July 2
Piloting
Selection of training for piloting | Identification of pilot training | SMC Leadership/Content Development team | bar: May 2
| Approval by Client | TWG | bar: May 2 to May 3
Piloting guide and assessment tool development | Prepare TOT guideline | Content Development team | bar: May 4
| Develop training assessment form, | Content Development team | bar: May 4 to June 1
ToT implementation | Introduction and selection of Master Trainers | GDAS | bar: June 2
| Hold TOT workshop for master trainers | National Consultant | bar: June 3
Cascade | Casecade training to district and province level academic supervisors, Share feedback and experiences of the participants with lead consultant. | Master Trainer | bar: June 4 to July 1
Closeout
Final Report | Draft and submit Final report | SMC | bar: July 4 to August 1
| Provide Final approval for report and material | AQLC | bar: August 1 to August 2